## PFC23-02
Projects [$4.50 rate] | Est. Charge | Approval of | Project | Project | Quarter | Cumulative | Amount of | Current | Variance
APPLICATION 16-01-C-00-FSD | Effective Date | Use Date | Start | Stop | Expenditures | Expenditures | Use Approval | Actual Cost | Approval/Est.
Ticketing Area Renovation | 2017-01-01 | 2016-11-21 | 2007-09-01 | 2012-01-01 | * | 5447120 | 5447120 | 5447120 | 0
Concourse Remodel | 2017-01-01 | 2016-11-21 | 2010-05-01 | 2012-12-01 | * | 3445360 | 3445360 | 3445360 | 0
Canopy Addition | 2017-01-01 | 2016-11-21 | 2011-06-01 | 2012-03-01 | * | 957199 | 957199 | 957199 | 0
Runway Intersection Replacement | 2017-01-01 | 2016-11-21 | 2009-07-01 | 2011-03-01 | * | 209987 | 209987 | 209987 | 0
Jetbridge 1 and 2 Replacement | 2017-01-01 | 2016-11-21 | 2009-07-01 | 2011-05-01 | * | 670129 | 670129 | 670129 | 0
Runway Safety Area (RSA) Project- Runway 3/21 | 2017-01-01 | 2016-11-21 | 2013-09-01 | 2016-09-01 | * | 331472 | 331472 | 331472 | 0
Security Checkpoint Renovation | 2017-01-01 | 2016-11-21 | 2014-11-01 | 2015-09-01 | * | 5947756 | 5947756 | 5947756 | 0
Taxiway B, B1, B2 and B3 Rehabilitation | 2017-01-01 | 2016-11-21 | 2015-05-01 | 2015-08-01 | * | 312042 | 312042 | 312042 | 0
Partial Rehab of Runway 3/21 Pavement and Blast Pads | 2017-01-01 | 2016-11-21 | 2015-05-01 | 2015-08-01 | * | 226756 | 226756 | 226756 | 0
Passenger Facility Charge Application- Number 1 | 2017-01-01 | 2016-11-21 | 2014-06-01 | 2016-02-01 | * | 44728 | 44728 | 44728 | 0
Rehabilitate Runway 21 Touchdown Zone Lighting | 2017-01-01 | 2016-11-21 | 2012-05-01 | 2013-02-01 | * | 20371 | 20371 | 20371 | 0
Total Use Approval for
APPLICATION 16-01-C-00-FSD |  |  |  |  | 0 | 17612920 | 17612920 | 17612920 | 0
Ticketing Area Renovation | [9 empty] | 0 | Total Builder's Risk Insurance paid for project
$5,447,120.00 Approved collection amount per RECORD OF DECISION
$5,447,120.00 Actual project cost/Airport amount
$0 EXCESS
Concourse Remodel
$3,445,360.00 Approved collection amount per RECORD OF DECISION
$3,445,360.00 Actual Project cost/Airport amount
$0 EXCESS
Canopy Addition
$957,199.00 Approved collection amount per RECORD OF DECISION
$957,199.00 Actual Project cost/Airport amount
$0 EXCESS
Runway Intersection Replacement
$209,987.00 Approved collection amount per RECORD OF DECISION
$209,987.00 Actual local airport share (5%) of AIP Project #3-46-0050-43-2011
$0 EXCESS
Jetbridge 1 and 2 Replacement
$670,129.00 Approved collection amount per RECORD OF DECISION
$670,129.00 Actual Project cost/Airport amount
$0 EXCESS
Runway Safety Area (RSA) Project - Runway 3/21
$331,472.00 Approved collection amount per RECORD OF DECISION
$331,472.00 Actual local airport share (5%) of AIP Project #3-46-0050-46/47-2013
$0 EXCESS
Security Checkpoint Renovation
$5,947,756.00 Approved collection amount per RECORD OF DECISION
$5,947,756.00 Actual Project cost/Airport amount
$0 EXCESS
Taxiway B, B1, B2, B3 Rehabilitation
$312,042.00 Approved collection amount per RECORD OF DECISION
$312,042.00 Actual local airport share (5%) of AIP Project #3-46-0050-049-2015
$0 EXCESS
Partial Rehab of Runway 3/21 Pavement and Blast Pads
$226,756.00 Approved collection amount per RECORD OF DECISION
$226,756.00 Actual local airport share (5%) of AIP Project #3-46-050-049-2015
$0 EXCESS
Passenger Facility Charge Application - Number 1
$44,728.00 Approved collection amount per RECORD OF DECISION
$44,728.00 Actual Project cost/Airport amount
$0 EXCESS
Rehabilitate Runway 3/21 Touchdown Zone Lighting
$20,371.00 Approved collection amount per RECORD OF DECISION
$20,371.00 Actual local airport share (5%) of AIP Project #3-46-0050-43-2011
$0 EXCESS
APPROVED APPLICATIONS | Impose Only | Impose & Use | Use | Total
APPLICATION 16-01-C-00-FSD | 0 | 17612920 | 0 | 17612920 | FAA closeout | Ongoing
Total Authority | 0 | 17612920 | 0 | 17612920
| Current Qtr. | Cumulative | MAX PFC16-01
PFC Revenue Received | 661505.61 | 14392124.83
Interest Earned on Impose Only Amount | 8813.83 | 106938.45
Total PFC Revenue Received | 670319.44 | 14499063.28
Expenditures on Approved PFC Projects | 0 | 17612920 | 17612920
Total Expenditures on Approved PFC Projects | 0 | 17612920
Project Payoff | Current Qtr. | Cumulative | Project Cost
Ticketing Area Renovation | 0 | 5447120 | 5447120
Concourse Remodel | 0 | 3445360 | 3445360
Canopy Addition | 0 | 957199 | 957199
Runway Intersection Replacement | 0 | 209987 | 209987
Jetbridge 1 and 2 Replacement | 0 | 670129 | 670129
Runway Safety Area (RSA) Project- Runway 3/21 | 0 | 331472 | 331472
Security Checkpoint Renovation | 670319.44 | 3437796.28 | 5947756
Taxiway B, B1, B2 and B3 Rehabilitation | 0 | 0 | 312042
Partial Rehab of Runway 3/21 Pavement and Blast Pads | 0 | 0 | 226756
Passenger Faciltiy Charge Application-Number 1 | 0 | 0 | 44728
Rehabilitate Runway 21 Touchdown Zone Lights | 0 | 0 | 20371
TOTAL | 670319.44 | 14499063.28 | 17612920
[5 empty] | CY | YTD TOTAL | BALANCE OF PFC
YEAR | 1STQTR | 2NDQTR | 3RDQTR | 4THQTR | TOTAL | CASH REC'D | FUNDS TO COLLECT
2017 | 541531.74 | 559978.33 | 606782.78 | 512306.05 | 2220598.9 |  | 14392124.83 | CASH REC'D
2018 | 592653.17 | 591513.35 | 568164.83 | 542779.47 | 2295110.82 |  | 106938.45 | INTEREST
2019 | 617458.74 | 598286.46 | 618684.44 | 618738.52 | 2453168.16 |  | 14499063.28 | TOTAL CASH
2020 | 548310.78 | 101637.22 | 268059.82 | 300911.43 | 1218919.25
2021 | 497531.79 | 580745.21 | 571501.4 | 586134.7 | 2235913.1
2022 | 700005.55 | 647475.66 | 642063.94 | 597444.58 | 2586989.73
2023 | 719919.26 | 661505.61 | 0 | 0 | 1381424.87
2024 | 0 | 0 | 0 | 0 | 0
2025 | 0 | 0 | 0 | 0 | 0 |  | 3113856.72 | Balance to Collect
2026 | 0 | 0 | 0 | 0 | 0
14392124.83